## Sheet1
Day | Module / Area | Work Description | Work Hours | Expected Output | Additional Information
Day 1 | Project Setup & Auth | Replace Bolt auth, integrate Laravel login/signup, route protection, session handling, Redux toolkit implementation | 8 | Working Sign In / Sign Up | All work inclued with ui and api with documentation
Day 2 | Dashboard | Project list page integration, fetch projects API, loading & empty states | 8 | Dashboard with project list
Day 3-4 | Project Creation – Setup | Project draft API, wizard state management, base project creation flow | 16 | Project draft flow ready
Day 5 | Document Upload (AI) | Document upload API, OpenAI integration setup, secure file storage | 8 | Document upload working
Day 6 | AI Auto-Fill | Document scan and auto-fill Project Details, Dates, Job Description with manual override | 8 | Auto-fill or manual entry
Day 7-8 | Wizard Forms | Project Details, Project Dates (dynamic), Job Description APIs and UI integration | 16 | Wizard steps saved
Day 9-10 | Contract & Contacts | Contract details, project contacts forms, CRUD APIs and listing | 16 | Contract & contacts saved
| County | Database creation, seeder added, api creation | 4
| Country | Database creation, seeder added, api creation | 4
| Quick Remedy | Deadline Calculation UI and api integration | 5
| Project Implementation | Tried to Implement database and file in Cpanel but not done. | 2
|  | Total Hours | 95
Upcoming weeks will cover remaining form steps:
1. project tasks forms and list
2. project summary
3. Project final step
4. Project view
5. Project Edit
Disclaimer:
This timeline excludes server configuration, file deployment, and server-side testing activities.